## Sheet1
Compliance table for conditions of consent RM190050
Condition number | Condition Wording | Date updated | Notes | Author
1 | The proposal is carried out substantially in accordance with the information and approved plans submitted with the application and held on file at the council.
2 | The consent holder keeps a copy of the decision on site when work starts and makes it avaliable on request to council staff.
3 | The consent holder shall ensure that cleanfilling is undertaken with the publication A guide to the management of Cleanfills by the MFE 2002.
4 | Prior to accepting cleafill material from off-site, the consent holder shall submit for approval to the Team Leader of Resource Consent a site management plan (SMP) for approval. The SMP shall outline the proposed operation of the cleanfilll, including the procedures and controls to manage the site, and at a minimun shall include descriptions of matters outlined in condition 4.
5 | CLG to be formed and meet on a three-monthly basis following the commencement of the consent. Invitations will be sent to CLG members at least 4 weeks prior to meeting. The minutes shall be provided within three (3) working days of the meeting occuring.
6 | Prior to submitting the SMP to HCC for approval, the consent holder shall provide a draft to the CLG and submitters and provide them with the oppurtunity to provide comment upon the document.
7 | Prior to accepting cleafill material from off-site the consent holder shall seal the access road internal to the site between the site gate and the site entrance kiosk.
8 | Within three months of the stage 3 operation commencing the consent holder shall install a portable wheel-wash on-site. In the event material tracks onto Coast Road, it must be swept clear within 12 hours of being deposited.
9 | No more than 75 trucks per day shall be permitted to access the site for the purpose of depositing cleanfill material.
10 | The consent holder will ensure that access to the site for the purpose of the cleanfill deposition is granted only to approved commerical operators.
11 | Within one month of completion of each sub-stage of the stage 3 filling, the consent holder shall ensure that the particular sub-stage is progressivley stabilised. The stage should be monitored and maintained until 80% grass cover has been establisihed.
12 | Noise from any cleanfill deposition activities (excluding emergency and construction works) shall not exceed the following levels when measured at or within the notional boundary of any dwelling existing at the time the consent is granted: a. Monday to Friday (excluding public holidays) 7.30 am to 5.00 pm – 50 dB LAeq b. Saturday (excluding public holidays) 7.30 am to 12.00 pm – 50 dB LAeq c. All other times - 40 dB LAeq d. 10.00 pm to 7.00 am (all days) – 75 dB LAfmax
13 | Site construction activites shall be assessed (and measured where appropriate) in accordance with NZS 6803: 1999 “Acoustics - Construction Noise"
14 | The consent holder shall notify the Resource Consents Team Leader and members of CLG of any constrctuion activites taking place and their expected duration, at least five working days prior to commencement of those activites. | 24.02.21 | The independent Auditor has advised that despite the authorisation of the sealing of the road by conditon 7, the consent holder should have notified the CLG that this was going to occur in December 2019. Therefore, this condition was breached back then. My intrepretation, was that since the sealing of the road was covered specifically by conditon 7 this was not a breach. Having been corrected by the auditor, I am now recording this as a breach in December 2019. Since then, this condition has not been breached. | Parvati Rotherham
15 | The noise management plan (NMP) prepared by Tonkin + Taylor Ltd (dated November 2017) shall be updated within two months of approval of this resource consent. Any subsequent changes to the operation of the cleanfill relevant to noise generation will require a review of the NMP.
16 | The consent holder shall undertake noise monitoring of the cleanfill within 30 days of work commencing withing stage 3 and thereafter at three month intervals. All monitoring results shall be made avaliable to Hutt City Council within two weeks of completion of each monitoring visit. | 24.02.21 | Noise monitoring reports have been supplied for July, September and December. These report were not supplied withing 2 weeks of the completion of monitoring. Consent holder cautioned on ensuring these report are provided within consented timeframes next time | Parvati Rotherham
17 | The cleanfill shall only operate within the hours of Monday to Friday 7.30am - 5.00pm and Saturday 7.30am - 12.00pm, excluding public holidays
18 | The consent holder shall ensure that the operation is managed in a manner to ensure that no dust nuisance occurs beyond the boundary of the site. Measures for control will be ountlined in the SMP, and must include the presence of a watercraft on-site at all times that filing occurs.
19 | That if the consent holder finds taonga on the site, the consent holder must conatct iwi representatives, the Heritahe Mew Zealand and Council within 24 hours. All work in the area must stop immediately and may not resume until iwi representatives and Council staff have carried out a site inspection and the council gives it approval.
20 | The final batter slopes shall be designed and certified by a suitably qualified geotechnical engineer and certification shall be provided to the Team Leader Resource Consent within three months of the cleanfill reaching capcity.
21 | The consent holder shall manage cleanfill activites to generally avoid the placement of concrete and building rubble and other material not easily compacted in the part of the site affected by the 1:100 year floodway, unless appropriate rock armouring is installed on the southern edge of the fill area.
22 | By 19 June 2022, cleanfilling shall cease, with restoration of the site in accordance with the Environmental Restoration Plan to commence during the next planting season following approval of the Envrionmental Restoration Plan.
23 | The consent holder shall submit an Environmental Restoration Plan for stage 3 of the cleanfill to the Team Leader Resource Consents for approval within three months of thee cleanfill reaching capcitiy or by the lapse date. The environmental restoration plan shall include measures to grass or landscape any exposed areas and ensure the site is left in a sutiable conditon condition to enable use of the site as a reserve in fututre. The plan will have regard to guidance from GWRC ‘Restoration Planting – A Guide to Planning Restoration Planting Projects in the Wellington Region’
24 | The consent holder shall control weeds and maintain the plants in accordance with the procedures set out in the Environmental Restoration Plan for three years.
25 | The consent holder shall engage an independent audit of the site on a six (6) monthly basis to ensure that the site is operating in accordance with the conditions of consent.
26 | Hutt City Council may review any or all conditons of the consent by giving notice of its intention to do so on a six monthly basis for any of the following reasons: a. To review the adequacy of any plan and/or monitoring requirements, and if necessary, amend these requirements outlined in this consent. b. To deal with any adverse effects on the environment that may arise from the exercise of this consent; and which are appropriate to deal with at a later stage. c. To enable consistency with any relevant District Plan(s) or any National Environmental Standards or Regulations. d. The review of conditions shall allow for the deletion or amendment of conditions of this consent; and the addition of such new conditions as are shown to be necessary to avoid, remedy or mitigate any significant adverse effects on the environment